## Agile Backlog
Agile Backlog
Project | Financial_Multi_Agent | Owner | Shantanu Patil | Timeline | Sep 16, 2026 – Oct 19, 2026; Latest Git: 2026-10-19
Sprint | Story ID | User Story / Task | Acceptance Criteria | Status | Priority | Owner
Sprint 1 | US-001 | PDF Document Loading & Text Extraction | PDF text extraction functions load single and multi-page annual reports using pdfplumber/PyPDF2 with graceful error handling. | Done | High | Shantanu Patil
Sprint 1 | US-002 | Document Text Chunking & Segmentation | Extracted document text is split into recursive chunks preserving sentence boundaries and section context for indexing. | Done | High | Shantanu Patil
Sprint 1 | US-003 | SentenceTransformers Embedding Generation | Document chunks are converted into dense vector embeddings using local transformer models (all-MiniLM-L6-v2). | Done | High | Shantanu Patil
Sprint 1 | US-004 | ChromaDB Vector Store Integration | Local persistent ChromaDB vector store is initialized to persist embeddings and chunk metadata with vector similarity search capability. | Done | High | Shantanu Patil
Sprint 1 | US-005 | DocumentAgent Implementation | DocumentAgent class encapsulates document loading, text parsing, chunking, and ChromaDB upsert into a cohesive agent interface. | Done | High | Shantanu Patil
Sprint 2 | US-006 | FastAPI Backend & Document Upload Endpoint | REST API /upload endpoint receives PDF files, validates payload format and size, and persists document to uploads directory. | Done | High | Shantanu Patil
Sprint 2 | US-007 | SQLite Database Schema for Sessions & Documents | SQLite schema initialized with research_sessions and documents tables supporting relational audit tracking and session isolation. | Done | High | Shantanu Patil
Sprint 2 | US-008 | ExtractionAgent for Financial Metrics Extraction | ExtractionAgent parses core metrics (revenue, net profit, operating profit, EPS) and normalizes messy currency strings via clean_number. | Done | High | Shantanu Patil
Sprint 2 | US-009 | Financial Ratios Calculation Engine | Automated calculation of profit margin, operating margin, ROE, ROA, and debt ratios with division-by-zero protection. | Done | High | Shantanu Patil
Sprint 2 | US-010 | Windows Startup Scripts & Virtual Environment Setup | Convenience scripts (run_app.cmd, run.ps1) activate Python virtual environment and launch backend API and Streamlit UI servers. | Done | Medium | Shantanu Patil
Sprint 3 | US-011 | RedFlagAgent Risk Review & Pattern Analysis | RedFlagAgent identifies audit qualifications, debt surges, margin contractions, and unusual disclosures with grounded document snippets. | Done | High | Shantanu Patil
Sprint 3 | US-012 | LangGraph Multi-Agent Workflow Orchestration | State graph pipeline in workflow/graph.py coordinates document processing, extraction, risk review, and reporting execution. | Done | High | Shantanu Patil
Sprint 3 | US-013 | ResearchAgent Semantic Vector Retrieval & Grounded Q&A | ResearchAgent performs similarity search against ChromaDB and answers user finance queries with retrieved citations and Gemini synthesis. | Done | High | Shantanu Patil
Sprint 3 | US-014 | ComparisonAgent Cross-Company Analysis | ComparisonAgent queries indexed documents across companies and periods, producing side-by-side metric comparison tables. | In Progress | High | Shantanu Patil
Sprint 3 | US-015 | Streamlit Multi-Page Interactive Web Application | Streamlit frontend provides Dashboard, Research Chat, Company Comparison, Reports, and Document Management views. | Done | High | Shantanu Patil
Sprint 4 | US-016 | Google Gemini API Integration & Model Fallback Chain | Centralized Gemini client with automated fallback chain (gemini-3.5-flash, gemini-3.5-flash-lite, gemini-flash-lite-latest) on quota limits. | Done | High | Shantanu Patil
Sprint 4 | US-017 | Low-Level Architecture Documentation & Mermaid Diagrams | Comprehensive Low-Level Design (LLD), component inventory, and architecture sequence diagrams added to README. | Done | Medium | Shantanu Patil
Sprint 4 | US-018 | Multi-Company Report Generation & ReportLab PDF Export | ReportAgent generates consolidated multi-company summaries and compiles downloadable formatted PDF reports using ReportLab. | Done | High | Shantanu Patil
Sprint 4 | US-019 | Page-Wise PDF Text Segmentation | Enhanced PDF parser and chunker to extract page numbers and preserve pagination context in embeddings. | Done | Medium | Shantanu Patil
Sprint 5 | US-020 | Fix ComparisonAgent Multi-Chunk Metric Extraction (DEF-001) | Concatenate all ordered chunk texts per document prior to metric extraction instead of using the final loop variable. | Planned | High | Shantanu Patil
Sprint 5 | US-021 | Automated Regression Test Suite Implementation (DEF-002) | Implement pytest regression test suite covering all agents, workflow routing, and API endpoints. | Planned | Medium | Shantanu Patil
Sprint 5 | US-022 | Advanced Tabular Financial Statement Parser | Enhance parser to extract complex multi-column tables directly from balance sheets and cash flow statements. | Planned | Low | Shantanu Patil
Notes | Sprints 1 through 4 are verified from Git commit history (2026-09-16 to 2026-10-19) under Infosys Springboard Virtual Internship. Status Done signifies implemented and verified locally. In Progress indicates active implementation with open defect DEF-001 under review. Planned represents prioritized backlog items for Sprint 5.