## Defect Tracker
Defect Tracker
Project | Financial_Multi_Agent | Owner | Shantanu Patil | Timeline | Sep 16, 2026 – Oct 19, 2026; Latest Git: 2026-10-19
Defect ID | Date | Module | Defect Description | Severity | Priority | Status | Owner | Suggested Resolution
DEF-001 | 2026-10-19 | ComparisonAgent | Metric extraction uses the loop's last text chunk instead of combining all chunks for each document; comparison metrics can be wrong or unavailable. | High | High | Open | Shantanu Patil | Join each document's ordered chunks (ordered_chunks) and pass the combined text to ExtractionAgent.extract_metrics; add a multi-chunk regression test.
DEF-002 | 2026-10-19 | Testing Framework | No automated regression test suite was found in the current repository following test script refactoring in commit 2311aae. | Medium | Medium | Open | Shantanu Patil | Add standardized automated pytest test suite for agents, workflow routing, API validation, and report generation.
DEF-003 | 2026-10-11 | Backend API (/research) | Research endpoint failed to resolve document_id when scoped to a specific document because SQLite documents table UUID differed from ChromaDB indexed document_id. | High | High | Closed | Shantanu Patil | Added SQL lookup in backend/main.py to map document UUID to filename and resolve corresponding ChromaDB indexed document ID (resolved in commit 21accb5).
DEF-004 | 2026-10-11 | ExtractionAgent | Financial year extraction regex failed on annual reports formatted as Form 10-K or integrated report <year>. | Medium | Medium | Closed | Shantanu Patil | Extended regex pattern to support (annual report¦10-k¦form 10-k¦integrated report) followed by year (resolved in commit 21accb5).
DEF-005 | 2026-10-11 | RedFlagAgent | Currency parsing in _metric_number failed on Rs. and INR prefixes, and parenthesized negative values (100) were not parsed as negative floats. | Medium | Medium | Closed | Shantanu Patil | Updated regex to strip Rs./INR and properly applied negative sign -abs(number) for parenthesized values (resolved in commit 21accb5).
DEF-006 | 2026-10-11 | Frontend UI (Research Chat) | Streamlit research page crashed with selectbox error if session state contained a document label from a previously loaded session that no longer exists. | Medium | Medium | Closed | Shantanu Patil | Added option validation to check if session state value exists in current document options, falling back to All matching documents (resolved in commit 21accb5).
DEF-007 | 2026-10-11 | LLM Client (gemini_client) | Google Gemini API calls failed with fatal error when primary model encountered quota exhaustion (429/ResourceExhausted) or 404 deprecation without fallback. | High | High | Closed | Shantanu Patil | Implemented candidate model fallback chain (gemini-3.5-flash, gemini-3.5-flash-lite, gemini-3.1-flash-lite, gemini-flash-lite-latest) with exponential backoff (resolved in commit 21accb5).
DEF-008 | 2026-09-23 | Database / API | Document upload endpoint failed to link uploaded PDFs to active research session and lacked document metadata persistence. | High | High | Closed | Shantanu Patil | Added documents table to SQLite schema with foreign key relation to research_sessions and updated upload handler to store metadata (resolved in commits 0f15a09, aa5c8b0).
Notes | DEF-001 and DEF-002 are confirmed open defects in the active codebase. DEF-003 through DEF-008 are historical defects verified from Git commit diffs (21accb5, 0f15a09, aa5c8b0). All dates, modules, and resolutions match actual repository code and commit history.